MONGOLIA CIRCULAR BATTERY INITIATIVE

# BATTERY DIAGNOSTICS, TESTING, AND
CRITICAL MINERALS RECOVERY
RESEARCH CENTER PROJECT

Building the foundation for a safe, traceable, circular battery system in Mongolia

| Project initiator | Mongolia Circular Battery Initiative (MCBI) |
| --- | --- |
| Project lead | Enkhtsetseg Shirendev, Founder and CEO |
| Implementation site | Mongolia — site to be selected based on technical and safety assessment |
| Duration | 18 months (preparation, pilot operations, evaluation) |
| Document status | Proposal for partnership, funding, and technical discussion |
| Date | August 2026 |

Important note: This project does not establish a metal-extraction plant at this stage. It builds pilot capacity for collection, safe storage, diagnostics, sorting and classification, data recording, and standard operating procedures.

# PROJECT SUMMARY

| Indicator | Description |
| --- | --- |
| Project name | Establishment of a battery diagnostics, testing, and critical minerals recovery research center |
| Sector | Hazardous waste management, circular economy, green technology |
| Overall goal | Establish the practical foundation of a national system for safely collecting, diagnosing, classifying, and tracing batteries |
| Direct beneficiaries | Citizens, importers, repair/service providers, waste operators, government agencies, research and educational institutions |
| Key deliverables | Pilot center; SOPs; digital records; pilot collection network; training; data; policy recommendations |
| Duration | 18 months |
| Funding form | Grants, public-private partnership, industry participation, equipment and technical support |

# Abbreviations

| Abbreviation | Meaning |
| --- | --- |
| MCBI | Mongolia Circular Battery Initiative |
| EPR | Extended Producer Responsibility |
| SOH | State of Health (of a battery) |
| SOC | State of Charge |
| SOP | Standard Operating Procedure |
| BMS | Battery Management System |
| PPE | Personal Protective Equipment |
| ESS | Energy Storage System |

# 1. Project Summary

MCBI’s ultimate goal is to establish a battery diagnostics, testing, and critical minerals recovery research center in Mongolia, and this project is its first stage — a collection, diagnostics, and sorting laboratory.

As the use of electric vehicles, energy storage systems, electric tools, and portable devices grows in Mongolia, the need to safely manage the resulting flow of end-of-life batteries is increasing. However, practical capacity to record batteries by type, chemistry, technical condition, and hazard level, to evaluate reuse potential on an evidence basis, and to route them to the appropriate next destination remains insufficient.

Over 18 months, the project will establish one pilot center and a limited collection network to test the receive–quarantine–safe storage–diagnose–classify–record workflow. The center will not forcibly dismantle, shred, or chemically extract metal from batteries. Instead, it will place each battery into a decision category: reusable, requiring transfer to specialized processing only, or hazardous/damaged and to be quarantined.

Core value of the project: It builds real data, safety practices, trained personnel, and an institutional roles model in Mongolia, making it possible to base the next investment decision on evidence rather than assumption.

# 2. Context and Problem Rationale

## 2.1 Pressing Issues

More than 77% of Mongolia’s territory is currently affected by land degradation, and an uncontrolled flow of end-of-life batteries risks accelerating this degradation further.

Mongolia currently has no legal framework for mandatory battery collection, take-back, or Extended Producer Responsibility (EPR) for manufacturers/importers, so the flow continues to accumulate unregulated.

Mongolia has not yet developed full-scale domestic production capacity to separate, assay, and purify rare earth elements and other critical minerals.

Consolidated data on the actual volume, type, location, and age profile of battery waste is scarce.

Mixing damaged or charged batteries with ordinary waste, or storing them in unsuitable locations, carries the risk of fire, thermal runaway, and hazardous substance release.

Capacity to distinguish, by technical criteria, between batteries that can be reused and those that require reprocessing is weak.

The roles of importers, users, repair shops, transporters, and waste operators, and the mechanism for exchanging information among them, are unclear.

Treating an undiagnosed battery outright as either “waste” or “valuable raw material” can lead to poor safety and economic decisions.

## 2.2 Project Rationale

Before a large-scale reprocessing plant can be planned outright, the battery flow, chemical composition, SOH, logistics, safety practices, and market channels need to be tested in practice. The pilot center will close this information gap and form the basis for the next decisions on policy, standards, and investment.

## 2.3 Policy and Permitting Principles

In implementing the project, applicable Mongolian requirements on the environment, waste, hazardous substances, fire safety, occupational safety, construction, and transport will be verified with the relevant authorities. Activities requiring a permit will begin only after the permit has been obtained. Final classification, licensing, and reporting obligations will be confirmed with legal and technical advisors.

# 3. Goal and Objectives

## 3.1 Overall Goal

Lay the foundation of a national system for safely, responsibly, and traceably managing end-of-life batteries, and validate the model for a pilot collection, diagnostics, and sorting center (laboratory).

## 3.2 Specific Objectives

Conduct baseline research on battery sources, types, volumes, and movement.

Develop the technical, safety, and site design of the pilot center, and map out the permitting pathway.

Test, within a limited scope, the system for receiving, transporting, quarantining, and storing batteries.

Carry out visual inspection, voltage, temperature, and insulation checks, and — where possible — BMS data readout and SOH assessment, under standard procedures.

Assign each battery a unique digital ID/QR code and record its origin, analysis, classification, and transfer.

Deliver a training package for operators, emergency services, repair providers, and importers.

Develop recommendations on EPR, standards, financing, and next-stage capacity, based on pilot data.

# 4. Scope and Limitations

| In Scope | Out of Scope |
| --- | --- |
| Baseline research and source mapping | Declaring the country’s total waste volume from unverified estimates |
| Safe receiving, packaging, and temporary storage | Uncontrolled stockpiling of batteries in ordinary warehouses |
| Non-destructive diagnostics and classification | Disassembling packs without safety validation |
| QR/digital traceability records | Collecting personal data beyond what is necessary |
| Transfer to an approved partner | Shredding, smelting, or hydrometallurgical processing |
| Training, SOPs, and emergency preparedness | Transporting hazardous waste without authorization |

Decision principle: A battery of uncertain condition is never classified as reusable. Safety takes precedence over economic return.

# 5. Target Groups and Stakeholders

| Stakeholder | Role and Involvement | Expected Benefit |
| --- | --- | --- |
| Government agencies | Policy, permitting, oversight, data exchange | Real data for decision-making |
| Importers, distributors | Take-back points, information, financial participation | Preparation for EPR, reduced risk |
| Repair and service providers | Detection, initial quarantine, transfer | Safety, a responsible channel |
| Citizens, herders, organizations | Proper hand-over, providing information | Reduced fire and pollution risk |
| Universities, laboratories | Methodology, research, human resources | Real case studies, research data |
| Waste operators | Logistics, storage, approved transfer | New services, capacity |
| Emergency/fire services | Emergency planning, training, advice | Improved risk preparedness |

# 6. Implementation Methodology and Work Packages

## WP1. Baseline Research and Regulatory Mapping (Months 1–3)

Conduct surveys, interviews, and voluntary data collection on battery sources.

Develop a provisional taxonomy by chemistry, form factor, and use-case category.

Produce a matrix of relevant laws, permits, standards, and reporting requirements.

Establish site-selection criteria and carry out a preliminary risk assessment.

## WP2. Center Design, Permitting, and Procurement (Months 2–7)

Plan the flow between clean/receiving/quarantine/diagnostics/storage/emergency zones.

Develop requirements for fire detection, thermal monitoring, ventilation, spill containment, and access control.

Prepare equipment technical specifications, obtain three price quotes, and evaluate procurement options.

Secure permits, insurance, and service contracts.

## WP3. SOPs, Training, and Emergency Preparedness (Months 4–9)

SOPs for receiving, rejecting, labeling, packaging, transporting, quarantining, diagnosing, classifying, and recording data.

Response procedures for thermal runaway, smoke, mechanical damage, electrolyte leakage, and electrical hazards.

Initial and refresher operator training; practical drills; competency assessment.

## WP4. Pilot Collection and Diagnostics (Months 8–15)

Test hand-over channels with a small number of partner collection points.

Register each battery under a unique ID, recording photos, origin, date, chemistry, and hazard status.

Carry out non-destructive diagnostics and assign an A/B/C/D decision classification.

Maintain chain-of-custody until transfer to an approved next holder.

## WP5. Evaluation, Policy Recommendations, and Scale-up Mapping (Months 14–18)

Analyze cost, safety performance, collection/return rates, and the classification breakdown.

Assess EPR financing, importer participation, and deposit/return scheme options.

Estimate next-stage capacity requirements from actual flow data.

Present the final report, policy recommendations, and a phased investment plan.

# 7. Technical Operating Model

| Step | Action | Output |
| --- | --- | --- |
| 1. Advance Notification | Obtain information on source, type, damage, and quantity | Preliminary accept/reject decision |
| 2. Receiving | Documentation, photos, weight, labeling, external inspection | Unique ID and record |
| 3. Quarantine | Isolate units that are damaged, overheating, or leaking | Hazard level |
| 4. Diagnostics | Voltage, temperature, and insulation checks; BMS/SOH readout where possible | Technical result |
| 5. Classification | Decide using pre-approved criteria | A/B/C/D classification |
| 6. Storage | Segregate by chemistry, condition, and hazard level | Safe temporary storage |
| 7. Transfer | Confirm documentation, recipient, date, weight | Chain-of-custody record |

## 7.1 Proposed Decision Classification

| Category | Description | Next Destination |
| --- | --- | --- |
| A | Passes diagnostics and can be reused in a validated application | Further engineering validation / second-life testing |
| B | Requires repair or detailed module-level evaluation | Approved specialist partner |
| C | Not reusable; routed to material-recovery stream | Approved recycling operator |
| D | Damaged, overheating, leaking, or of undetermined high risk | Quarantine and special handling |

Classification thresholds will be set according to battery chemistry, manufacturer technical data, test-equipment precision, intended use, and professional engineering judgment. A single, universal SOH threshold will not be applied to all batteries.

# 8. Equipment and Infrastructure Requirements

| Category | Indicative Requirement | Notes |
| --- | --- | --- |
| Safe receiving | Segregation bins, fire-resistant cabinets/dedicated storage, labeling, scales | Final selection based on risk assessment |
| Monitoring and detection | Thermal cameras, temperature sensors, gas/smoke detection, CCTV | Whether 24/7 alerting is required to be determined by design |
| Electrical diagnostics | Insulation tester, multimeter, battery analyzer/cycler, CAN/BMS interface | Protection matched to voltage and chemistry |
| Workstations | Insulating mats, tools, lifting/handling equipment, barriers | Ergonomics and high-voltage zoning |
| PPE and emergency equipment | Eye, face, hand, respiratory, and arc-flash protection; spill kits | Aligned with SOPs and hazard classification |
| Information system | ID/QR printer, scanner, database, backups | With access levels and an audit trail |
| Infrastructure | Ventilation, electrical protection, grounding, emergency exits | Subject to authorized design and inspection |

Procurement condition: The exact equipment model, capacity, and cost will be confirmed based on the scope of battery types covered, facility design, supplier proposals, and an authorized safety assessment.

# 9. Implementation Structure and Governance

| Level/Role | Key Responsibility |
| --- | --- |
| Steering Committee | Strategy, partnerships, budget, major risks, stage-gate decisions |
| Project Director | Overall leadership, partnerships, reporting, funder relations |
| Project Manager | Day-to-day planning, procurement, scheduling, contracts, reporting |
| Technical Lead | Design, equipment, test methodology, classification criteria |
| EHS/Environmental Officer | Risk assessment, SOPs, training, incidents, compliance |
| Data and Traceability Officer | ID/QR, data quality, privacy, reporting dashboard |
| Finance/Procurement | Budget, documentation, tendering/selection, audit |
| External Advisor/Evaluator | Legal, fire, construction, laboratory methodology, final evaluation |

## 9.1 Decision-Making

Monthly implementation meetings and quarterly Steering Committee oversight will be held.

Any operator has the authority to stop work in the event of a serious safety violation.

Major budget changes, scope expansions, and the addition of new battery chemistries will be approved through a change-control procedure.

Every incident, violation, and near-miss will be logged, with root cause and corrective action tracked to closure.

# 10. Timeline

| Activity | Months 1–3 | Months 4–6 | Months 7–9 | Months 10–12 | Months 13–15 | Months 16–18 |
| --- | --- | --- | --- | --- | --- | --- |
| Baseline research and mapping | ● |  |  |  |  |  |
| Design and permitting | ● | ● | ● |  |  |  |
| Procurement and installation |  | ● | ● |  |  |  |
| SOPs and training |  | ● | ● | ● |  |  |
| Collection network testing |  |  | ● | ● | ● |  |
| Diagnostics and classification pilot |  |  | ● | ● | ● |  |
| Data analysis |  |  |  | ● | ● | ● |
| Policy recommendations and scale-up mapping |  |  |  |  |  | ● |

## Stage Gates

| Gate | Decision Condition |
| --- | --- |
| G1 — Proceed to Design | Site shortlist, regulatory matrix, and preliminary risk assessment approved |
| G2 — Begin Installation | Permitting pathway clear, design approved, procurement review complete |
| G3 — Begin Receiving Batteries | SOPs, training, emergency plan, insurance, and equipment inspection complete |
| G4 — Expand Pilot | Initial operations safety review, data quality, and partner performance satisfactory |
| G5 — Next Stage | Decision based on final evaluation, actual flow volumes, unit costs, and regulatory conditions |

# 11. Expected Results and Indicators

| Result | Indicator | 18-Month Target* | Means of Verification |
| --- | --- | --- | --- |
| 1. Center Capacity | Operational, inspected pilot center | 1 center | Handover certificate, inspection |
| 2. Safety | Approved SOPs | At least 10 | SOP register |
| 3. Human Resources | People trained and having passed assessment | ≥20 | Attendance, assessment records |
| 4. Collection Channel | Active partner points | 3–5 | Contracts, transfer records |
| 5. Traceability | Share of intake with unique ID | 100% | Database |
| 6. Diagnostics | Share of intake assessed per protocol | ≥90%** | Test records |
| 7. Safety | Serious injury/uncontrolled incidents | 0 | Incident log |
| 8. Policy Deliverables | Final recommendations and scale-up plan | 2 documents | Report |

* Targets to be confirmed after baseline research. ** Calculated for batteries that are receivable and within instrument scope.

## 11.1 Monitoring and Evaluation

Baseline indicators will be established in Months 1–3 and targets approved by the Steering Committee.

Monthly operational reports and quarterly financial and KPI reports will be produced.

Data quality will be checked for duplicates, missing fields, and weight/count discrepancies.

A mid-term internal evaluation will be conducted in Months 9–10, and an external/joint final evaluation in Months 17–18.

Personal data such as gender, age, and disability status will be used only where necessary and authorized, and will be separately safeguarded.

# 12. Budget Structure and Financing

Final figures will be determined by site, design, permitting requirements, battery voltage/chemistry, equipment technical specifications, and supplier quotes. The table below is the basic framework for developing the budget together with donors, partners, and investors.

| No. | Budget Category | Basis of Estimate | Amount (MNT) |
| --- | --- | --- | --- |
| 1 | Baseline research, detailed technical-economic assessment | Person-months, travel, data | TBD |
| 2 | Design, permitting, legal/safety consulting | Contracts, fees, certification | TBD |
| 3 | Facility, renovation, engineering infrastructure | m², lease/renovation, ventilation, electrical | TBD |
| 4 | Safe storage, fire and monitoring systems | Technical specification, 3 quotes | TBD |
| 5 | Diagnostic and measurement equipment | Technical specification, calibration | TBD |
| 6 | IT, QR, database, cybersecurity | Licensing, development, hardware | TBD |
| 7 | PPE, packaging, transport, consumables | Unit price × planned quantity | TBD |
| 8 | Human resources, training, professional services | Person-months, training days | TBD |
| 9 | Communications, stakeholder engagement, materials | Events, publications, translation | TBD |
| 10 | Monitoring, audit, insurance | Contracted services | TBD |
| 11 | Contingency | 5–10% of approved direct costs | TBD |
|  | TOTAL |  | TBD |

## 12.1 Budget Approval Principles

Where feasible, at least three comparative quotes will be obtained for any given procurement category.

Supplier safety record, warranty, training, spare parts, calibration, and repair terms will be evaluated alongside price.

Project staff salaries, taxes, insurance, VAT, and currency risk will be costed separately.

Contingency funds will be used only against an approved change request.

In-kind contributions from the organization and partners (facilities, equipment, expert time, information) will be valued and recorded.

## 12.2 Potential Financing Package

Government support in the form of policy, infrastructure, and permitting.

Co-financing from importers, manufacturers, and distributors in preparation for EPR.

Grants from international organizations, development banks, and climate/circular-economy funds.

In-kind support from technology suppliers in the form of equipment, training, and licensing.

Methodological and laboratory validation support from universities and research institutions.

# 13. Risk Management

| Risk | Likelihood/Impact | Mitigation Measures | Owner |
| --- | --- | --- | --- |
| Permitting delays | Medium/High | Early mapping; pre-consultation with authorities; phased contracting | Project Director |
| Thermal runaway/fire | Low–Medium/Very High | Advance notification; quarantine; thermal monitoring; SOPs; drills; stop-work authority | EHS Lead |
| Misclassification | Medium/High | Dual verification; calibration; approved criteria; default to Category D when uncertain | Technical Lead |
| Insufficient input flow | Medium/Medium | Partner agreements; phased procurement; modular capacity | Project Manager |
| Missing/lost data | Medium/High | Mandatory fields; audit trail; backups; access controls | Data Officer |
| Cost escalation/currency | High/Medium | Price quotes; contingency; bundled procurement; currency clauses | Finance |
| Unauthorized downstream holder | Low/High | Due diligence; license verification; chain-of-custody; audit rights | Manager |
| Public misperception | Medium/Medium | Transparent communication; grievance channel; incident-communication protocol | Communications |

# 14. Environment, Social, and EHS

## 14.1 Minimum Safety Requirements

A battery without a completed risk assessment will not be admitted to the main diagnostics zone.

Batteries that are damaged, overheating, swollen, or leaking will be immediately flagged and quarantined.

High-voltage work will require authorization, lockout-tagout procedures, and a two-person rule.

PPE will be selected based on hazard assessment, with fit and usage records maintained.

Emergency exits, communications, first aid, and fire response will be coordinated with the relevant authorities.

Children and unauthorized persons will not be permitted into the operational area.

## 14.2 Environmental Protection

Flooring, storage, and spill-containment solutions will be designed to block pathways for electrolyte and other contamination.

Separate records will be kept for batteries, contaminated PPE, spill-response materials, and packaging.

Processing that uses water or generates wastewater is outside the scope of the pilot.

Transport distances, packaging, and load units will be logged to assess logistics impact.

## 14.3 Social Safeguards and Grievance Resolution

Local residents, staff, and partner organizations will have a confidential channel for raising concerns related to safety, labor, the environment, and information. A procedure for logging grievances, assigning an owner, resolving them within a set timeframe, and retaining evidence of closure will be approved at project start-up.

# 15. Data and Battery Passport Pilot

| Data Category | Core Fields |
| --- | --- |
| Identification | Unique ID, QR code, intake date, source type |
| Physical Data | Battery type, form factor, weight, manufacturer/model where available |
| Chemical Data | Chemistry as confirmed by label/documentation; unknown status |
| Hazard Status | Damage, overheating, swelling, leakage, insulation status |
| Diagnostics | Voltage, temperature, test method, instrument, calibration, operator, result |
| Decision | A/B/C/D classification, rationale, person who confirmed |
| Movement | Storage location, transfer date, recipient, documentation |
| Audit | User who made the change, date, previous/new value |

The information system will apply data minimization, role-based access, regular backups, a change-history log, defined retention periods, and a deletion procedure. A battery’s QR code will not expose personal or commercially confidential information to the public.

# 16. Communication and Knowledge-Dissemination Plan

| Target Group | Key Message | Channel/Product | Frequency |
| --- | --- | --- | --- |
| Citizens | Don’t put batteries in ordinary trash; don’t tamper with a damaged battery | Infographics, social media, hand-over instructions | Throughout the pilot |
| Importers/Service providers | Advance notification, packaging, and transfer requirements | Training, checklists, contracts | Kick-off + quarterly |
| Government agencies | Flow data, risk, regulatory evidence | KPI reports, technical meetings | Quarterly |
| Professional community | Methodology, lessons learned, further research | Technical seminars, briefs | Semi-annual |
| Donors/Partners | Progress, budget, risk, results | Progress and final reports | Per contract |

# 17. Sustainability and Scale-up Pathway

Post-pilot sustainability will be planned so as not to depend solely on project grant funding. The financial model will assess revenue sources — including importer/EPR fees, diagnostic services, partnership agreements, training, research services, and income from approved material flows — subject to legal and market review.

| Stage | Condition | Key Decision |
| --- | --- | --- |
| 0. Preparation | Permits, partners, site, financing | Go/No-Go |
| 1. Pilot Center | 18 months of safety performance and data | Approve service model |
| 2. Network Expansion | Stable flow, unit costs, partner performance | Add regional points/capacity |
| 3. Pre-processing Assessment | Sufficient volume, permits, market, proven safe technology | Modular pre-processing |
| 4. Material Recovery | Proven feedstock, water/energy/environmental clearance, financial viability | Domestic/regional technology partnership |

Across these stages, MCBI remains interested in collaborating at the research level with advanced critical-minerals-separation technology institutions such as IOCB Prague, and in testing their technology under Mongolian conditions. This collaboration is not yet formally confirmed, but represents one possible direction for the Pre-processing Assessment (Stage 3).

Scale-up rule: Each next stage will be decided based on the actual volumes, incident record, unit costs, legal compliance, and buyer/processor assurances of the preceding stage.

# 18. Conditions for Project Success

Early engagement of the relevant authorities and a clear permitting pathway.

Contracts with importers, service providers, and operators who have a genuine commitment to supply battery flow.

A professional team capable of independently monitoring safety.

Supplier assurance of training, calibration, repair, and spare parts for equipment.

An unbroken chain-of-custody record.

A culture of reporting results without exaggeration and disclosing incidents and lessons learned transparently.

Clarity on the post-pilot financing mechanism and institutional ownership.

# 19. Conclusion and Partnership Proposal

The pilot center proposed by MCBI is a foundational investment for launching Mongolia’s battery circular system in a realistic, safe, and phased way. Rather than promising a large-scale plant upfront, the project first builds an understanding of battery flows, manages risk, and develops diagnostic capacity, traceable data, trained people, and institutional cooperation.

MCBI proposes to work with government agencies, importers, technology suppliers, universities, laboratories, development organizations, investors, and professional waste operators in the following areas:

A site, permitting, and regulatory working group;

Technical partnership on equipment, methodology, and training;

A pilot collection network and battery-flow agreements;

Digital records, QR codes, and data standards;

Financing, in-kind support, and joint research;

Independent safety and results evaluation.

In the long run, managing battery flows properly will not only reduce environmental risk but also form the foundation for bringing the mineral wealth needed for the future energy transition back to Mongolia with added value. All of this begins with reliably establishing the pilot center and building the first data, practices, and trust — and that is precisely the core of MCBI’s proposal.

# APPENDIX 1. LOGICAL FRAMEWORK

| Level | Statement | Indicator | Assumption |
| --- | --- | --- | --- |
| Impact | Battery-waste risk is reduced and the foundation of a circular system is established | Pilot data is used in government/sector decisions | Policy engagement continues |
| Outcome | Safe collection, diagnostics, and traceability systems are operating | Completeness of ID, diagnostics, and transfer records | Partners remain consistently engaged |
| Output 1 | Pilot center and equipment | 1 operational center | Site and permits are resolved |
| Output 2 | SOPs and a trained team | ≥10 SOPs; ≥20 people | Experts and training resources are available |
| Output 3 | Data and policy recommendations | QR records; 2 final documents | Data quality is adequate |

# APPENDIX 2. SITE-SELECTION CHECKLIST

☐ Suitability of zoning and permitting

☐ Distance and risk conditions relative to housing, schools, and other sensitive receptors

☐ Emergency-vehicle access, emergency exits, and isolation capability

☐ Flooring, drainage, and spill-containment conditions

☐ Ventilation, electrical capacity, grounding, and voltage protection

☐ Physical separation of quarantine, diagnostics, and storage

☐ CCTV, access control, and 24/7 alarm capability

☐ Transport access and a safe loading/unloading area

☐ Potential for future modular expansion

☐ Lease/ownership, insurance, and total operating cost

# APPENDIX 3. BATTERY INTAKE FORM — KEY FIELDS

| Category | Field |
| --- | --- |
| Source | Organization/source type; contact; transfer documentation |
| Battery | Manufacturer; model; serial number if available; application; chemistry |
| Quantity | Number of units; total weight; unit weight if available |
| Condition | Whether State of Charge (SOC) is known; damage; swelling; overheating; leakage; odor |
| Intake | Date/time; operator; photos; ID/QR; packaging |
| Decision | Accepted/rejected; quarantine; reason; person confirming |

# APPENDIX 4. INFORMATION NEEDED TO FINALIZE THE BUDGET

City/district for the center, candidate facility floor area, and ownership/lease terms.

Battery types to be covered in the first 18 months: portable, 12/24V, EV module/pack, ESS, etc.

Planned maximum voltage, weight, dimensions, and peak monthly intake volume.

Whether pack disassembly is included — assumed out of scope for this version.

Required diagnostic precision, number of cycle-test channels, and BMS protocol coverage.

Hazard classification, fire-engineering design, and insurance requirements.

Transport radius, number of collection points, and packaging turnover stock.

Staffing numbers, shifts, salaries, training, and any need for international experts.

Project currency, tax/VAT, import, customs, delivery, calibration, and warranty terms.

Post-pilot operator, ownership, and revenue model.

# APPENDIX 5. OPEN ITEMS TO BE CONFIRMED

| Item | Working Assumption in This Proposal | Party to Confirm |
| --- | --- | --- |
| Site | Mongolia; final city/site not yet selected | Project initiator + local authorities |
| Legal Classification | All applicable permits will be mapped in advance | Legal advisor + relevant authority |
| Battery Scope | Limited at pilot start, expanded based on risk assessment | Technical Committee |
| Volume | To be set after baseline research | Project team + partners |
| Budget | Figures left blank pending quotes and design | Finance + procurement |
| Downstream Processor | To be confirmed via license, capacity, and contract | Project Manager |
| Second-life | Not used without separate engineering validation | Technical Committee |

— END OF DOCUMENT —